## Worksheet
Task | Start Date | End Date | Duration (Days) | Responsible | Status
Market Research & Analysis | 2024-03-15 | 2024-03-31 | 17 | Marketing Team | On Track
Product Roadmap Finalization | 2024-04-01 | 2024-04-10 | 10 | Product Manager | In Progress
UI/UX Design Phase | 2024-04-11 | 2024-05-15 | 45 | Design Team | Scheduled
Development Sprint 1 | 2024-05-16 | 2024-06-13 | 38 | Engineering Team | Planned
QA Testing & Bug Fixing | 2024-06-14 | 2024-07-05 | 23 | Quality Assurance | Not Started
Go-Live & Launch Campaign | 2024-07-06 | 2024-07-15 | 10 | Operations & Marketing | Pending Approval
Workflow Optimization - Startup Style Gantt Chart