## Worksheet
Task | Start Date | End Date | Duration (Days) | Responsible | Status
Project Initiation | 2024-01-01 | 2024-01-15 | 15 | Project Manager | Completed
Requirements Gathering | 2024-01-16 | 2024-02-15 | 30 | Business Analysts | In Progress
Design Phase | 2024-02-16 | 2024-03-31 | 46 | UI/UX Team | Planned
Development Phase | 2024-04-01 | 2024-06-30 | 90 | Development Team | Not Started
Testing & QA | 2024-07-01 | 2024-07-31 | 31 | QA Team | Not Started
Deployment & Launch | 2024-08-01 | 2024-08-15 | 15 | IT Operations | Planned
Post-Launch Review | 2024-08-16 | 2024-08-31 | 16 | Project Manager | Planned