## Worksheet
Task | Start Date | End Date | Duration (Days) | Responsible Team | Status
Project Kickoff & Planning | 2024-03-01 | 2024-03-10 | 10 | Project Management Team | Completed
Requirements Gathering & Analysis | 2024-03-11 | 2024-04-05 | 35 | Product & UX Team | In Progress
Design Phase (UI/UX) | 2024-04-06 | 2024-05-15 | 40 | Design Team | Planned
Development & Coding | 2024-05-16 | 2024-07-31 | 77 | Engineering Team | Not Started
Testing & Quality Assurance | 2024-08-01 | 2024-08-31 | 31 | QA Team | Not Started
User Training & Documentation | 2024-09-01 | 2024-09-15 | 15 | Support & Operations Team | Not Started
Go-Live & Post-Implementation Review | 2024-09-16 | 2024-09-30 | 15 | All Teams | Not Started