## Worksheet
Task ID | Task Name | Start Date | End Date | Status | Duration (Days) | Responsible Team
T001 | Requirement Gathering | 2024-03-01 | 2024-03-15 | In Progress | 15 | Product Management
T002 | Solution Design2024-03-16 | 2024-04-05 | Planned | 21 | Engineering Team
T003 | Development Phase (Phase 1)2024-04-062024-05-15Pending Approval | 41 | Development Team
T004 | Testing & QA Validation2024-05-162024-06-15Scheduled | 31 | QA Team
T005 | Deployment & Go-Live2024-06-162024-06-30Pending Review | 15 | Operations Team
T006 | Post-Launch Review & Optimization2024-07-012024-07-31Pending Start | 31 | Analytics & Support Team