## Worksheet
Task | Start Date | End Date | Duration (Days) | Status | Responsible Party | Progress (%)
Requirements Gathering | 2024-03-01 | 2024-03-15 | 15 | Completed | Project Manager | 100
Design Phase (UI/UX) | 2024-03-16 | 2024-04-10 | 35 | In Progress | UX Designer | 65
Development (Frontend) | 2024-04-11 | 2024-05-30 | 60 | Planned | Frontend Developer | 0
Development (Backend) | 2024-04-11 | 2024-06-15 | 85 | Planned | Backend Developer | 0
Testing & QA | 2024-06-16 | 2024-07-15 | 30 | Not Started | QA Engineer | 0
Deployment & Go-Live | 2024-07-16 | 2024-07-31 | 16 | Not Started | DevOps Team | 0
Post-Launch Review | 2024-08-01 | 2024-08-10 | 10 | Planned | Project Manager | 0