## Worksheet
Week | Activity | Start Date | End Date-th> | Responsible | Duration (Days) | Status
Week 1 | Project Kickoff & Stakeholder Alignment | 2024-04-01 | 2024-04-07 | J. Smith | 7 | On Track
Week 2 | Requirements Gathering & Validation | 2024-04-08 | 2024-04-14 | A. Johnson | 7 | In Progress
Week 3 | Design Phase & Wireframe Approval | 2024-04-15 | 2024-04-21 | M. Brown | 7 | On Track
Week 4 | Development Sprint 1 | 2024-04-22 | 2024-04-28 | T. Davis | 7 | Pending Review
Week 5 | Testing & Bug Resolution | 2024-04-29 | 2024-05-05 | L. Wilson | 7 | Delayed (Pending)
Week 6 | Final Review & User Acceptance Testing | 2024-05-06 | 2024-05-12 | S. Garcia | 7 | On Track