## Worksheet
Workflow Step | Responsible Party | Due Date | Status | Priority Level | Notes/Actions
Requirement Gathering | Project Manager & Stakeholders | 2024-04-15 | Completed | High | Finalize scope document and validate with client.
Process Mapping | Business Analyst | 2024-04-22 | In Progress | Medium | Refine workflows using BPMN; review with operations team.
Tool Selection & Integration | IT Lead & DevOps | 2024-05-05 | Pending | High | Evaluate automation tools; finalize integration roadmap.
Training & Onboarding Plan | HR & Operations | 2024-05-15 | Completed | Medium | Schedule sessions for all departments.
Performance Monitoring | Quality Assurance Team | 2024-06-01 | In Progress | High | Set KPIs and baseline metrics for process efficiency.