## Worksheet
Workflow Step | Responsible Party | Due Date | Status | Remarks
Initiation Request | Project Manager | 2024-04-01 | Completed | Approved by Stakeholder Group
Process Mapping | Operations Analyst | 2024-04-15 | In Progress | Draft review scheduled for 04/13
Workflow Design | Lead Designer | 2024-05-01 | Pending | Waiting for process mapping finalization
Stakeholder Review | Project Steering Committee | 2024-05-15 | Not Started | Meeting to be scheduled
Implementation Plan | IT & Operations Team | 2024-06-01 | Blocked | Pending approval from Compliance Office