## Worksheet
Workflow Step | Responsible Party | Due Date | Status | Notes
Initiation | Project Manager | 01/15/2024 | Completed | Workflow approved by client.
Requirement Gathering | Business Analyst | 02/01/2024 | In Progress | Client feedback pending.
Design Phase | UX Designer | 02/15/2024 | Pending | Final approval required from client.
Development | Development Team | 03/10/2024 | Not Started | Waiting for design approval.
Testing & QA | QA Engineer | 04/05/2024 | Not Started | No test plan yet.
Deployment | IT Operations | 04/15/2024 | Not Started | Server readiness pending.
Post-Deployment Review | Project Manager | 05/01/2024 | In Progress | Feedback collection underway.