## Worksheet
Workflow Step | Responsible Party | Input Requirements | Output Deliverables | Timeline (Days) | Status | Dependencies | Risk Assessment | Approval Needed?
Initiate Workflow | Project Manager | Business case, stakeholder list, scope document | Workflow initiation approval, project charter | 1 | Completed | None | Low | Yes
Define Process Map | Process Analyst | Current state documentation, stakeholder interviews | Visual workflow diagram, process map (PDF/Excel) | 3 | In Progress | Initiate Workflow | Medium | No
Identify Bottlenecks | Operations Team | Process map, historical performance data | Bottleneck analysis report, root cause summary | 2 | Not Started | Define Process Map | High | Yes
Propose Optimization Measures | Process Improvement Team | Bottleneck report, resource availability | Optimization plan (with KPIs), suggested changes | 4 | Not Started | Identify Bottlenecks | Medium | Yes
Implement Changes | IT & Operations Teams | Optimization plan, training materials | Updated process workflow, change log | 5 | Not Started | Propose Optimization Measures | High | Yes
Monitor & Measure Performance | Performance Analyst | KPIs, baseline data | Performance dashboard, monthly report | Ongoing (Monthly) | Not Started | Implement Changes | Low to Medium | Yes
Review & Refine | Project Manager & Stakeholders | Performance data, user feedback | Refinement plan, updated workflow version | 1-2 (Quarterly) | Not Started | Monitor & Measure Performance | Medium | Yes