## Worksheet
Workflow Step | Responsible Party | Timeline (Days) | Key Deliverables | Status | Notes/Remarks
Initiation & Requirement Gathering | Project Manager & Stakeholders | 5 | Workflow scope document, stakeholder list | Completed
Process Mapping & Analysis | Business Analyst & Operations Team | 7 | Flowchart, pain points report | In Progress | Pending input from IT department.
Tool & Technology Selection | IT Lead & Tech Consultant | 6 | Software evaluation report, vendor recommendations | Planned | Final decision expected in Q3.
Design & Prototyping | UX Designer & Development Team | 10 | Wireframes, interactive prototype | Not Started | Final approval required from Product Owner.
Implementation & Deployment | DevOps & Project Manager | 14 | Live system rollout, training materials | Scheduled | Phased rollout starting in Week 8.
Monitoring & Optimization | Operations Team & Analysts | Ongoing | Performance metrics, KPI reports | Not Started | Monthly reviews scheduled.