## Worksheet
Workflow Step | Responsible Party | Deadline | Status | Notes / Actions
Workflow Initiation | Project Manager | Day 1 | Completed | All stakeholders on board; kickoff meeting held.
Requirement Gathering | Business Analyst | Day 5 | In Progress | Interviews with department heads; documentation in progress.
Process Mapping | Process Designer | Day 8 | Pending | Draft workflow diagrams to be reviewed by stakeholders.
Stakeholder Review | Project Steering Committee | Day 10 | Not Started | Final approval needed before moving to implementation.
Implementation Planning | IT Team & Operations Lead | Day 15 | Planned | Resource allocation and timeline finalized.
Pilot Launch | Operations Lead | Day 20 | Not Started | Limited rollout to test performance and feedback.
Full Deployment | Project Manager & IT Team | Day 30 | Planned | All departments to be onboarded with updated workflow.
Performance Review & Optimization | Project Manager & Analytics Team | Day 45 | Not Started | KPI tracking; feedback collection to refine future iterations.