## Worksheet
Workflow Step | Responsible Party | Deadline | Status | Notes
Requirement Gathering | Project Manager | 2024-03-15 | Completed | Initial stakeholder interviews conducted.
Process Mapping | Business Analyst | 2024-03-20 | In Progress | Draft flowchart in review.
Process Improvement Plan | Operations Team | 2024-04-05 | Pending | Needs feedback from cross-functional team.
Stakeholder Approval | Chief Operating Officer | 2024-04-15 | Not Started | Formal sign-off required.
Implementation Phase | IT & Development Team | 2024-05-01 | Blocked | Pending budget approval.