## Worksheet
Workflow Step | Responsible Party | Timeline (Days) | Status | Notes
Initiation & Requirement Gathering | Product Owner & Stakeholders | 5 | Completed | All requirements documented and reviewed.
Process Mapping & Analysis | Process Analyst | 7 | In Progress | Current workflows mapped; bottlenecks identified.
Optimization Design | Lead Designer & Engineering | 10 | Planned | Proposed changes to reduce cycle time by 30%.
Pilot Implementation | Operations Team | 14 | Not Started | To be launched in Q2 with 2 departments.
Full-Scale Rollout & Training | Training & HR | 21 | Pending Approval | Final approval needed from C-suite.