## Worksheet
Task | Owner | Due Date | Status | Priority | Notes
Define Workflow Objectives | Jane Doe | 2024-04-10 | In Progress | High | Align with team goals and stakeholder expectations.
Map Current Processes | John Smith | 2024-04-15 | Not Started | Medium | Document existing steps using process flow diagrams.
Identify Bottlenecks | Sarah Lee | 2024-04-20 | Planned | High | Analyze cycle times and performance metrics.
Propose Workflow Improvements | Mike Chen | 2024-05-05 | Not Started | High | Present draft improvements to team for review.
Conduct Team Review & Feedback | Team Leads | 2024-05-10 | In Progress | Medium | Collect input from cross-functional teams.
Finalize & Implement Changes | Operations Manager | 2024-05-20 | Not Started | High | Roll out new workflow with training and monitoring.