## Worksheet
Workflow Step | Responsible Party | Duration (Days) | Input Required | Output Produced | Validation Criteria | Dependencies | Automated Checks?
Inventory Audit Initiation | Operations Manager | 1 | Audit schedule, access rights | Audit plan document | Approved by Finance Lead | None | Yes
Stock Count Execution | Inventory Staff | 3 | Barcode scanners, inventory list | Physical count report | Matches system records within 2% variance | Audit Initiation complete | Yes
Data Entry & System Update | IT Support Team | 1 | Count report, system access | Updated inventory database | All records verified and reconciled | Stock Count Execution complete | Yes (automated)
Discrepancy Review & Root Cause Analysis | Quality Assurance Lead | 2 | Count report, system logs | Root cause analysis report | Clear root cause identified and documented | Data Entry & System Update complete | Yes (with flags)
Corrective Action Plan Implementation | Operations Manager | 1-3 | Root cause report, action plan | Implemented corrective actions | Actions completed and verified by QA | Discrepancy Review complete | Yes (automated alerts)
Final Verification & Closure | Audit Committee | 1 | Corrective action logs, reports | Final closure report with audit sign-off | All actions closed and approved | Corrective Action Plan complete | Yes (digital approval)