## Worksheet
Workflow Step | Responsible Party | Input Requirements | Output Deliverables | Timeline (Days) | Status | Notes
Inventory Audit Initiation | Operations Manager | Access to system, inventory logs | Audit checklist, data summary report | 3 | On Track
Stock Categorization | Inventory Analyst | Audit report, item database | Categorized inventory list | 5 | In Progress | Reviewing obsolete items.
Reorder Point Analysis | Supply Chain Specialist | Demand history, lead time data | Reorder point recommendations | 4 | Planned | Pending demand forecast update.
Workflow Review & Validation | Process Owner | Categorized list, reorder points | Approved workflow document | 2 | Scheduled | Final approval needed from Finance.
Implementation & Training | IT & Operations Team | Approved workflow, updated system access | Trained staff, implemented workflow | 7 | Not Started | Training schedule to be finalized.