## Worksheet
Workflow Step | Responsible Party | Deadline (YYYY-MM-DD) | Status | Documentation Required | Approval Needed?
Inventory Audit Initiation | Operations Manager | 2024-01-15 | In Progress | Yes - Audit Plan Document | No
Inventory Categorization | Category Team Lead | 2024-02-10 | Pending | Yes - Categorization Matrix | Yes
Stock Reconciliation | Warehouse Supervisor | 2024-03-05 | Not Started | Yes - Reconciliation Report | Yes
Supplier Review & Validation | Procurement Officer | 2024-04-15 | Planned | Yes - Supplier Evaluation Form | Yes
Workflow Process Mapping | Operations Analyst | 2024-05-30 | Not Started | Yes - Process Flow Diagram | Yes
Optimization Recommendations | Senior Operations Manager | 2024-06-20 | Pending | Yes - Action Plan & Rationale | Yes
Implementation Roadmap Approval | Finance & Operations Board | 2024-07-10 | Not Started | Yes - Final Implementation Plan | Yes
Performance Review Post-Implementation | Operations Manager | 2024-09-30 | Not Started | Yes - KPI & Efficiency Report | Yes
Annual Workflow Optimization Inventory Template ¦ Version 2.1 ¦ Prepared for Operational Efficiency