## Worksheet
Workflow Step | Responsible Party | Input Requirements | Output Deliverables | Timeline (Days) | Approval Needed? | Status
Inventory Audit Initiation | Operations Manager | Access to inventory database, staff checklist | Audit report summary | 3 | Yes | Pending
Inventory Categorization | Inventory Analyst | Audit report, product classification schema | Categorized inventory list (by type, shelf life) | 5 | No | In Progress
Stock Reconciliation | Warehouse Supervisor | Physical count records, digital system logs | Reconciliation report with variances | 7 | Yes | Planned
Workflow Review & Adjustment | Process Optimization Team | Reconciliation report, audit findings | Optimized workflow document | 4 | Yes (Senior Management) | Not Started
Implementation & Training | Operations & HR Teams | Updated workflow document, training materials | Staff trained records, updated SOPs | 6 | Yes (Team Lead) | Scheduled
Performance Monitoring | Operations Manager | Monthly KPI dashboards, system logs | Monthly performance review report | Ongoing | Yes (Quarterly) | Active