## Worksheet
Workflow Step | Responsible Party | Due Date | Status | Action Required
Requirement Gathering | Project Manager & Stakeholders | 2024-04-15 | Completed | N/A
Workflow Design & Process Mapping | Business Analysts | 2024-04-25 | In Progress | Finalize process flow and submit for review.
Tool Selection & Integration Planning | IT Department | 2024-05-10 | Pending | Present options and evaluate compatibility with existing systems.
Staff Training & Change Communication | HR & Department Heads | 2024-05-30 | Not Started | Develop training materials and schedule sessions.
Pilot Implementation & Feedback Loop | Operations Team | 2024-06-15 | Planned | Run pilot in one department and collect feedback.
Full-Scale Deployment & Monitoring | All Departments & Support Team | 2024-07-30 | Not Started | Deploy workflow across all units and monitor KPIs.