## Worksheet
Workflow Step | Responsible Party | Deadline | Status | Dependencies | Actions Required
Project Initiation | Project Manager | 2024-04-01 | Completed | - | Documentation reviewed and approved.
Requirements Gathering | Business Analysts | 2024-04-15 | In Progress | Project Initiation | Finalize stakeholder inputs and validate requirements.
Design & Planning | UI/UX Team | 2024-05-10 | Pending | Requirements Gathering | Finalize wireframes and process flow diagrams.
Development Phase | Engineering Team | 2024-06-15 | Not Started | Design & Planning | Begin coding with version control setup.
Testing & QA | Quality Assurance | 2024-07-10 | Not Started | Development Phase | Conduct unit, integration, and user testing.
Deployment | DevOps Team | 2024-07-25 | Not Started | Testing & QA | Deploy to production with rollback plan.
Post-Deployment Review | Project Manager | 2024-08-05 | Not Started | Deployment | Collect feedback and document lessons learned.