## Worksheet
Workflow Step | Responsible Party | Deadline | Status | Actions Required
Client Request Received | Customer Service Team | Within 24 hours of request | Completed | Document verified and logged into system.
Requirement Analysis | Project Manager & Analysts | By Day 3 | In Progress | Finalize scope and deliverables list.
Proposal Development | Design & Pricing Team | <>By Day 5Pending Approval | Submit draft proposal for review.
Client Approval | Client Representative | By Day 7 | Not Started | Send proposal for sign-off; track feedback.
Contract Finalization | Legal & Finance Teams | By Day 10 | Pending | Review terms, finalize contract.
Project Kickoff Meeting | All Stakeholders | By Day 12 | Planned | Schedule and conduct kickoff session.