## Worksheet
Workflow Step | Responsible Party | Timeline (Days) | Key Deliverable | Dependencies | Risk & Mitigation
Loan Application Receipt | Customer Service Team | 1 | Digital receipt confirmation sent via email | None | No system failure; backup email server in place
Initial Credit Check | Credit Risk Department | 2 | Credit score report and risk assessment summary | Application receipt completed | Delay due to data latency; cache updates every 30 minutes
Underwriting Review | Loan Underwriter Team | 3 | Approval or denial decision with rationale | Credit check results available | Manual override process for edge cases; supervisor review required
Documentation Collection | Customer Service Team | 2 | Complete loan package uploaded to system | Underwriting decision issued | Missing documents flagged automatically; automated reminder sent
Contract Finalization | Legal & Contracts Team | 1 | Signed contract version stored and shared | All documentation complete and verified | Electronic signature not recognized; fallback to physical signatory
Loan Disbursement | Finance & Operations Team | 1 | Funds transferred to borrower account | Contract signed and approved | Payment delay due to bank processing time; real-time monitoring enabled
Post-Disbursement Follow-Up | Customer Success Team | 3 | First contact with borrower after disbursement | Funds received and verified | <Borrower unresponsive; automated escalation to manager