## Worksheet
Date | Task Description | Responsible Team | Estimated Hours | Actual Hours | Cost (USD) | Status | Next Action Date
2024-04-01 | System Audit and Process Mapping | IT Operations & Finance Team | 12 | 10.5 | 1,200.00 | Completed | 2024-04-15
2024-04-05 | Vendor Contract Review & Cost Analysis | Finance & Procurement | 8 | 7.2 | 850 | In Progress | 2024-04-18
2024-04-10 | Workflow Automation Pilot Launch | Operations & IT | 15 | 14.8 | 1,800.00 | Completed | 2024-04-25
2024-04-15 | Performance KPI Review & Reporting Setup | Finance & Analytics Team | 6 | 5.8 | 620 | Pending Approval | 2024-04-22