## Worksheet
Date | Work Task | Responsible Team | Status | Estimated Time (hrs) | Actual Time (hrs) | Remarks
01/15/2024 | Equipment Inspection (Machines A–C) | Maintenance Team | Completed | 4.5 | 4.2 | No abnormalities detected; all systems operating within threshold.
02/03/2024 | Software Patch Deployment | IT Operations | In Progress | 3 | -
03/12/2024 | Workflow Process Review | Operations & Planning | Completed | 6 | 5.8
04/10/2024 | Staff Training on New SOPs | HR & Training Dept | Completed | 5.5 | 5.3
05/08/2024 | System Performance Audit | IT & Analytics Team | Pending Review | 7 | -