## Worksheet
Date | Task | Assigned To | Status | Completion Time (hrs) | Remarks
2024-04-01 | Inspect all maintenance tools | John Smith | Completed | 2.5 | All tools accounted for; one missing screwdriver.
2024-04-01 | Update equipment logbook | Sarah Lee | Completed | 1.5 | All entries updated; included last inspection dates.
2024-04-02 | Conduct safety audit | Michael Brown | In Progress | - | Reviewing fire extinguisher locations and signage.
2024-04-03 | Train new technician on SOPs | Lisa Chen | Completed | 3 | Training completed; feedback collected.
2024-04-04 | Check HVAC system performance | David Kim | Pending | - | Scheduled for next week due to weather conditions.