## Worksheet
Month | Workflow Phase | Key Activities | Responsible Team | Target Completion Date | Budget Allocation (USD) | Status | Actual Cost (USD) | Variance (USD)
January | Process Audit | Review existing workflows, identify bottlenecks, document current procedures | Operations & Finance | 01/30/2024 | 5,000 | On Track | 4,800 | 200
February | Process Redesign | Redesign high-impact workflows using lean principles | Process Engineering & IT | 02/28/2024 | 15,000 | On Track | 14,500 | 500
March | Pilot Implementation | Deploy redesigned workflows in selected departments | Operations & Change Management | 03/31/2024 | 8,000 | On Track | 7,900 | 100
April | Full-Scale Rollout | Implement across all departments with training and support | All Departments & Leadership | 04/30/2024 | 30,000 | On Track | 29,600 | 400
May | Performance Review & Optimization | Measure KPIs, assess efficiency, identify further improvements | Analytics & Finance | 05/31/2024 | 6,000 | On Track | 5,800 | 200