## Worksheet
Month | Workflow Phase | Key Activities | Owner | Due Date | Status | Notes/Comments
January | Planning & Alignment | Define KPIs, review Q4 results, align team goals | Manager A | 2024-01-15 | Completed | Team aligned on Q1 priorities.
February | Process Mapping | Map current workflows, identify bottlenecks | Manager B | 2024-02-20 | In Progress | Initial maps completed; feedback requested.
March | Optimization & Testing | Test revised workflows, gather team input | Manager C | 2024-03-30 | Pending | No data yet; schedule review meeting.
April | Rollout & Monitoring | Deploy new workflows, track KPIs daily | Manager D | 2024-04-15 | Not Started | Training sessions scheduled for April 3.
May | Review & Feedback Loop | Analyze outcomes, document lessons learned | Manager A | 2024-05-25 | Planned | To be presented to leadership board.