## Worksheet
Month | Workflow Phase | Key Activities | Responsible Team | Deadline | Status | Notes & Observations
January | Initiation & Planning | Define workflow scope, stakeholder mapping, resource assessment | Strategy & Operations Team | Jan 15, 2024 | Completed | All stakeholders aligned; initial process map approved.
February | Process Design & Prototyping | Design workflow flowcharts, conduct mock runs, identify bottlenecks | Product & Process Design Team | Feb 28, 2024 | In Progress | Feedback from pilot team suggests refinement in approval steps.
March | Testing & Validation | Pilot implementation, data tracking, performance measurement | Engineering & QA Team | Mar 31, 2024 | Planned | Preparation of test scenarios and KPIs underway.
April | Full-Scale Rollout | Deploy workflow across departments, training sessions, monitoring | Operations & HR Team | Apr 30, 2024 | Not Started | Final feedback loop with end users scheduled for May.
May | Review & Optimization | Analyze performance data, adjust workflows, document best practices | Management & Analytics Team | Jun 10, 2024 | Pending | Metrics dashboard will be shared for review.