## Worksheet
Task | Responsible | Due Date | Status | Priority
Define Workflow Goals | John Doe | 2024-04-05 | In Progress | High
Map Current Processes | Jane Smith | 2024-04-10 | Pending | High
Identify Bottlenecks | Mike Lee | 2024-04-15 | Not Started | Medium
Propose Optimization Plan | Sarah Kim | 2024-04-20 | Draft | High
Review & Approve Changes | Team Lead | 2024-04-25 | Pending | Critical
Implement Workflow Updates | All Team Members | 2024-05-01 | Not Started | High