## Worksheet
Task | Duration (Days) | Start Date | End Date | Responsible Party | Status
Project Planning & Scope Definition | 5 | 2024-04-01 | 2024-04-05 | Freelancer A | Completed
Client Requirement Gathering | 7 | 2024-04-06 | 2024-04-12 | Freelancer B | In Progress
Resource Allocation & Team Setup | 3 | 2024-04-13 | 2024-04-15 | Freelancer C | Pending
Workflow Process Mapping | 6 | 2024-04-16 | 2024-04-21 | Freelancer A & B | Scheduled
Automated Task Assignment | 4 | 2024-04-22 | 2024-04-25 | Freelancer C | Not Started
Performance Metrics & KPIs Setup | 5 | 2024-04-26 | 2024-05-01 | Freelancer A | Planned