## Worksheet
Workflow Step | Responsible Party | Deadline | Status | Dependencies | Priority Level | Notes
Initiate Workflow | Project Manager | 2024-04-01 | Completed | None | High
Define Process Flow | Process Analyst | 2024-04-10 | In Progress | Initiate Workflow | Medium | Review with stakeholders.
Stakeholder Review | Operations Lead | 2024-04-15 | Pending | Define Process Flow | High | Final approval required.
Optimize Workflow | Data Analyst | 2024-04-25 | Not Started | Stakeholder Review | Critical | Analyze bottlenecks using KPIs.
Implement Changes | IT Team | 2024-05-05 | Blocked | Optimize Workflow | High | Pending system upgrades.
Monitor & Evaluate | Project Manager | 2024-05-30 | Not Started | Implement Changes | Medium | Track KPIs over 30-day period.