## Worksheet
Task | Owner | Due Date | Status | Priority
Define workflow objectives | John Smith | 2023-10-05 | In Progress | High
Map current workflow processes | Lisa Chen | 2023-10-10 | Not Started | Medium
Identify bottlenecks and inefficiencies | Michael Brown | 2023-10-15 | Not Started | High
Propose optimized workflow design | Sarah Lee | 2023-10-20 | Not Started | Medium
Review and approve revised workflow | Team Lead | 2023-10-25 | Not Started | High
Implement new workflow in production | IT Department | 2023-11-01 | Not Started | High
Monitor performance and collect metrics | Analytics Team | 2023-11-05 | Not Started | Medium