## Worksheet
Task | Owner | Due Date | Status | Priority | Notes
Define Workflow Objectives | John Smith | 2024-03-15 | In Progress | High | Align with client goals and current business processes.
Map Current Process Flow | Sarah Johnson | 2024-03-20 | Not Started | Moderate | Identify key steps, bottlenecks, and decision points.
Identify Process Improvements | Mike Chen | 2024-03-25 | Pending Review | High | Propose automation and elimination of redundant steps.
Stakeholder Workshop | Emily Davis | 2024-04-01 | Scheduled | Moderate | Present findings and gather feedback from key teams.
Finalize Optimized Workflow Design | John Smith | 2024-04-10 | Not Started | High | Integrate feedback and prepare documentation for rollout.