## Worksheet
Task | Owner | Due Date | Status | Priority | Dependencies | Notes
Define Workflow Objectives | Jane Smith | 2024-03-15 | In Progress | High |  | Align with business goals and stakeholder input.
Map Current Processes | John Doe | <"> 2024-03-20Not Started | Medium | Define Workflow Objectives | Document existing steps and pain points.
Identify Key Metrics | Lisa Chen | 2024-03-25 | In Progress | High | Map Current Processes | Determine KPIs for performance tracking.
Redesign Workflow Diagrams | Mike Wilson | 2024-04-01 | Not Started | High | Identify Key Metrics | Create visual flow with improved decision points.
Conduct Stakeholder Review | Team Lead | 2024-04-10 | Planned | Medium | Redesign Workflow Diagrams | Gather feedback and refine process.
Implement Changes & Monitor | All Team Members | 2024-04-30 | Not Started | High | Stakeholder Review | Track results using defined KPIs.