## Worksheet
Workflow Step | Owner | Start Date | Due Date | Status | Priority | Dependencies | Notes & Actions
Requirement Gathering | Project Manager | 2024-04-01 | 2024-04-15 | Completed | High | Stakeholder Interviews | Collect user needs and business goals.
Feasibility Analysis | Technical Lead | 2024-04-16 | 2024-04-30 | In Progress | High | Requirement Gathering | Evaluate technical and operational feasibility.
Design Phase | UX Designer | 2024-05-01 | 2024-05-15 | Planned | Medium | Feasibility Analysis | Create wireframes and UI mockups.
Development | Software Team | 2024-05-16 | 2024-06-30 | Pending | High | Design Phase | Implement features according to design.
Testing & QA | QA Lead | 2024-07-01 | 2024-07-15 | Not Started | High | Development | Conduct unit, integration, and user acceptance tests.
Deployment | DevOps Engineer | 2024-07-16 | 2024-07-20 | Pending Approval | Critical | Testing & QA | Deploy to production environment with rollback plan.
Post-Deployment Review | Project Manager | 2024-07-21 | 2024-07-31 | Not Started | Medium | Deployment | Gather user feedback and document lessons learned.