## Worksheet
Task | Owner | Due Date | Status | Priority | Dependencies | Estimated Time (hrs) | Notes
Define Workflow Goals | Jane Smith | 2024-04-05 | In Progress | High |  | 8 | Align with stakeholders and define KPIs.
Map Current Processes | Alex Johnson | <2024-04-10 | Not Started | Medium |  | 12 | Conduct process audits across departments.
Identify Bottlenecks | Sam Rivera | 2024-04-15 | Planned | High | Map Current Processes | 6 | Analyze data to locate inefficiencies.
Design Optimized Workflow | Maya Chen | 2024-04-25 | Not Started | High | Identify Bottlenecks | 16 | Create a visual flowchart with automation suggestions.
Implement Workflow Changes | Team Lead | 2024-05-10 | Not Started | Critical | Design Optimized Workflow | 24 | Roll out to selected departments with training.
Monitor & Measure Results | Jane Smith | 2024-05-30 | Not Started | Medium |  | 10 | Track KPIs and generate performance reports.