## Worksheet
Workflow Step | Responsible Party | Deadline | Status | Priority | Notes
Initiate Project Proposal | Project Manager | 2024-03-15 | Completed | High | Approved by stakeholders; sent to design team.
Finalize Requirements Document | Business Analyst | 2024-03-25 | In Progress | High | Review with legal team for compliance.
Develop Technical Design | Engineering Lead | 2024-04-10 | Pending | Medium | Waiting for feedback from QA team.
Conduct User Acceptance Testing | QA Team | 2024-04-25 | Not Started | High | Test plan approved; user training scheduled.
Deploy to Production | IT Operations | 2024-05-10 | Not Started | Critical | Post-deployment monitoring and rollback plan in place.
Post-Implementation Review | Project Manager | 2024-05-31 | Not Started | Medium | Collect feedback from users and stakeholders.