## Worksheet
Task | Owner | Due Date | Status | Priority | Progress (%) | Notes
Review Q3 Project Roadmap | Alex Johnson | 2024-06-15 | Completed | Medium | 100% | All milestones validated and approved.
Finalize Team Workflows | Sarah Kim | 2024-06-25 | In Progress | High | 75% | Feedback from QA team pending.
Conduct Stakeholder Alignment Meeting | Michael Lee | 2024-07-03 | Planned | Medium | 0% | Agenda to be circulated by June 28.
Optimize Reporting Dashboard | Jamie Rivera | 2024-07-10 | Pending Approval | High | 50% | Design mockups sent for review.
Update KPIs for Q3 | Tina Wu | 2024-07-15 | Completed | Low | 100% | Final KPIs aligned with department goals.