## Worksheet
Page | Workflow Step | Responsible Person | Deadline | Status | Notes/Actions
1 | Define Workflow Objectives | Project Manager | 2024-04-05 | In Progress | Align with stakeholders and document key goals.
2 | Map Current Processes | Operations Lead | 2024-04-10 | Not Started | Conduct process audit and document bottlenecks.
3 | Identify Improvement Areas | Quality Analyst | 2024-04-15 | Planned | Analyze data from step 2 to prioritize changes.
4 | Design Optimized Workflow | Process Designer | 2024-04-20 | Not Started | Create flowcharts and propose new sequence.
5 | Pilot Test New Workflow | Team Lead | 2024-04-25 | Not Started | Run test with a subset of team members.
6 | Evaluate Results & Scale | Project Manager | 2024-05-01 | Not Started | Review pilot outcomes and implement across teams.