## Worksheet
Task | Owner | Due Date | Priority | Status | Notes
Define Workflow Goals | Jane Smith | 2024-03-15 | High | In Progress | Align with department objectives and stakeholder input.
Map Current Processes | Mark Johnson | 2024-03-20High | Not Started | Document existing workflows using process diagrams.
Identify Bottlenecks | Lisa Chen | 2024-03-25 | Medium | Planned | Analyze data from past performance reports.
Propose Process Improvements | David Ross | 2024-04-05 | High | Not Started | Draft new workflow diagrams with efficiency metrics.
Review & Approve Changes | Sarah Williams | 2024-04-10 | High | Pending | Present to management for final approval.
Implement New Workflow | Team Lead | 2024-04-15 | Critical | Not Started | Roll out changes to all teams with training.