## Worksheet
Task | Owner | Start Date | End Date | Status | Priority | Dependencies
Define Workflow Requirements | Alex Chen | 2024-04-01 | 2024-04-10 | In Progress | High | None
Map Current Processes | Samira Patel | 2024-04-11 | 2024-04-18 | Planned | Medium | Define Workflow Requirements
Identify Bottlenecks | Jordan Lee | 2024-04-19 | 2024-04-25 | Planned | High | Map Current Processes
Design Optimized Workflow | Mia Thompson | 2024-04-26 | 2024-05-03 | In Progress | High | Identify Bottlenecks
Pilot New Workflow | Ryan Kim | 2024-05-04 | 2024-05-11 | Planned | Medium | Design Optimized Workflow
Evaluate Results & Iterate | All Team | 2024-05-12 | 2024-05-18 | Planned | High | Pilot New Workflow