## Worksheet
Workflow Step | Responsible Party | Due Date | Status | Priority | Notes/Comments
Initiate Workflow | Project Manager | 01/15/2024 | Completed | High | All prerequisites verified and approved.
Requirement Gathering | Business Analyst | 01/22/2024 | In Progress | High | Stakeholder interviews scheduled for 01/20.
Design Phase | UX Designer | 02/05/2024 | Pending | Medium | Final wireframes to be reviewed by PM.
Development Start | Development Team | 02/15/2024 | Not Started | High | Backend integration planned for 02/18.
Testing & QA | QA Lead | 03/05/2024 | Planned | High | Smoke and regression test cycles defined.
Deployment | DevOps Engineer | 03/15/2024 | Not Started | Critical | Rollout to production with rollback plan.