## Worksheet
Quarter | Workflow Phase | Key Activities | Owner(s) | Start Date | End Date | Status | Notes / Observations
Q1 (Jan–Mar) | Initiation & Planning | Define scope, identify stakeholders, draft workflow map | Project Manager, Department Heads | 2024-01-01 | 2024-03-31 | On Track
Q2 (Apr–Jun) | Design & Prototyping | Develop workflow models, conduct internal testing | UX Team, Engineering Lead | <2024-04-01 | 2024-06-30 | In Progress | Feedback from pilot group collected.
Q3 (Jul–Sep) | Implementation & Rollout | Deploy workflow in pilot department, train staff | Operations Manager, HR Team | 2024-07-01 | 2024-09-30 | Planned | Training sessions scheduled for all departments.
Q4 (Oct–Dec) | Evaluation & Optimization | Measure KPIs, gather user feedback, refine process | Data Analyst, Leadership Team | 2024-10-01 | 2024-12-31 | Not Started | Final report to be submitted Q1 2025.