## Worksheet
Workflow Step | Owner | Due Date | Status | Priority | Notes
Initiation Review | Project Manager | 2024-04-10 | In Progress | High | Confirm requirements with stakeholders.
Requirement Finalization | Business Analyst | 2024-04-15 | Pending | Medium | Review with legal team for compliance.
Design Approval | UX Lead | 2024-04-20 | Not Started | High | Finalize wireframes and user flows.
Development Start | Engineering Team | 2024-04-25 | Not Started | High | Begin sprint planning and code setup.
Testing & QA | QA Manager | 2024-05-05 | Not Started | Medium | Conduct unit and integration tests.
Deployment Review | DevOps Lead | 2024-05-10 | Not Started | High | Verify environment readiness and rollback plan.
Go-Live & Monitoring | Operations Team | 2024-05-12 | Not Started | High | Monitor performance and resolve issues in real-time.