## Worksheet
Task | Owner | Due Date | Status | Priority | Dependencies | Notes
Define Workflow Objectives | Team Lead | 2024-04-10 | In Progress | High | None | Align with business goals and stakeholder expectations.
Map Current Processes | Process Analyst | 2024-04-15 | Not Started | High | Define Objectives | Document existing workflows with process maps and interviews.
Identify Bottlenecks | Operations Team | 2024-04-20 | Not Started | Medium | Process Mapping Complete | Analyze cycle times and delays in each step.
Propose Workflow Improvements | Team Lead & Analyst | 2024-04-25 | Not Started | High | Bottleneck Analysis Complete | Draft new process flows with automation suggestions.
Review & Get Stakeholder Approval | Project Manager | 2024-05-01 | Not Started | High | Improvement Proposals Drafted | Present changes to key stakeholders for feedback and sign-off.
Implement Changes & Monitor | All Team Members | 2024-05-10 | Not Started | High | Stakeholder Approval Received | Roll out changes and track KPIs for performance improvement.