## Worksheet
Date | Activity | Responsible Team | Current Status | Time Estimate (hrs) | Actual Time (hrs) | Efficiency (%) | Key Bottleneck | Action Taken | Next Review Date
2024-04-01 | Client Onboarding Process Review | Operations & Sales | Completed | 8.5 | 7.2
2024-04-05 | Automated Approval Workflows Audit | IT & Compliance | In Progress | 12 | - | 85% | Manual override delays | Implemented auto-escalation rules | 2024-04-15
2024-04-10 | Cross-functional Task Alignment Meeting | Project Management Office | Completed | 6 | 5.8 | 97% | Communication gaps between teams | Introduced shared dashboard access | 2024-05-01
2024-04-15 | Performance Metrics Integration Review | Analytics & Finance | Pending Approval | 10 | - | - | Lack of real-time data feed | Awaiting integration from CRM | 2024-05-10
2024-04-20 | Process Redesign Workshop for Onboarding | Operations & Product | Scheduled | 15 | - | - | High volume during peak season | Finalizing draft workflow with stakeholders | 2024-05-05