## Worksheet
Date | Workflow Step | Responsible Party | Status | Estimated Time (hrs) | Actual Time (hrs) | Efficiency % | Notes
2024-04-01 | Requirement Gathering | Project Manager | Completed | 8 | 7.5 | 93.8% | No delays reported.
2024-04-03 | Design Approval | Design Team | In Progress | 12 | - | - | Waiting on client feedback.
2024-04-05 | Development Start | Engineering Team | Not Started | - | - | - | Blocked by missing specs.
2024-04-08 | QA Testing | QA Team | Completed | 15 | 14.2 | 94.7% | No critical bugs found.
2024-04-10 | Deployment | DevOps Team | Pending Review | 6 | - | - | Awaiting production sign-off.