## Worksheet
Task | Owner | Start Date | End Date | Status | Dependencies | Priority | Resources Required | Milestone?
Project Kickoff Meeting | John Doe | 2024-04-01 | 2024-04-02 | Completed | - | High | Project Manager, Stakeholders | Yes
Requirement Gathering | Jane Smith | 2024-04-03 | 2024-04-15 | In Progress | Kickoff Meeting | High | Business Analysts, Clients | Yes
Design Phase (UI/UX) | Alex Johnson | 2024-04-16 | 2024-05-05 | Planned | Requirement Gathering | Medium | Design Team, UX Researcher | Yes
Development Phase (Frontend) | Sam Lee | 2024-05-06 | 2024-06-15 | Not Started | Design Phase (UI/UX) | High | Frontend Developers, DevOps | No
Development Phase (Backend) | Taylor Wong | 2024-05-06 | 2024-06-15 | Not Started | Design Phase (UI/UX) | High | Backend Developers, QA Team | No
Testing & Quality Assurance | Mia Patel | 2024-06-16 | 2024-07-10 | Planned | Development Phase (Frontend & Backend) | High | QA Engineers, Test Automation Tools | Yes
User Training & Onboarding | Chris Brown | 2024-07-11 | 2024-07-15 | Not Started | Testing & QA | Medium | Training Team, Help Desk | Yes
Go-Live & Deployment | Jordan Kim | 2024-07-16 | 2024-07-18 | Not Started | User Training & Onboarding | High | DevOps, IT Operations | Yes
Post-Go-Live Review & Optimization | All Team Members | 2024-07-19 | 2024-07-30 | Planned | Go-Live & Deployment | Medium | Project Manager, Data Analysts | Yes