## Worksheet
Task | Owner | Start Date | End Date | Status | Resource Allocation | Dependencies
Project Initiation & Scope Finalization | Jane Doe | 01/01/2024 | 01/31/2024 | In Progress | Project Manager, Business Analyst | -
Stakeholder Workshops & Requirements Gathering | Mark Smith | 02/01/2024 | 02/15/2024 | Planned | Business Analysts, UX Designer | Project Initiation & Scope Finalization
Workflow Design & Process Mapping | Sarah Lee | 03/01/2024 | 03/28/2024 | Planned | Process Engineers, Operations Lead | Stakeholder Workshops & Requirements Gathering
Technology Stack Selection & Integration Planning | David Chen | 04/01/2024 | 04/30/2024 | In Progress | IT Lead, DevOps Engineer | Workflow Design & Process Mapping
Pilot Phase Implementation & Testing | Lisa Park | 05/01/2024 | 06/15/2024 | Not Started | Development Team, QA Engineers | Technology Stack Selection & Integration Planning
Full-Scale Deployment & User Training | James Wilson | 07/01/2024 | 08/31/2024 | Planned | Operations Team, Training Specialists | Pilot Phase Implementation & Testing
Performance Review & Continuous Improvement Planning | Anna Taylor | 09/01/2024 | 10/31/2024 | Not Started | Analytics Team, Process Owner | Full-Scale Deployment & User Training
Annual Project Plan – Workflow Optimization